## BLANK Software Dev Plan
Project Plan
Sudoku Class Project - Group D: Maintained By Robert
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN DAYS |  |  | START DATE | FINISH DATE | DURATION | PCT OF TASK COMPLETE | 9/4-9/8 |  |  |  |  | 9/9-9/15 |  |  |  |  | 9/16-9/22 |  |  |  |  | 9/23-9/29 |  |  |  |  | 9/30-10/6 |  |  |  |  | 10/7-10/13 |  |  |  |  | 10/14-10/20 |  |  |  |  | 10/21-10/27 |  |  |  |  | 10/28-11/3 |  |  |  |  | 11/4-11/10 |  |  |  |  | 11/11-11/17 |  |  |  |  | 11/18-11/24 |  |  |  |  | 11/25-12/1 |  |  |  |  | 12/2-12/8 |  |  |  |  | 12/9-12/15
|  |  | ESTIMATE | COMPLETED | REMAINING |  |  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Brainstorming/Requirement Specification |  | 19 | 19 | 0 |  |  |  | 100%
1.1 | Introduction | Robert, Jason, Nika | 5 | 5 | 0 | 2024-09-04 | 2024-09-08 | 5 | 100% | bar: 9/4-9/8 W to 9/4-9/8 F
1.2 | Storyboards | Robert, Jason, Nika | 7 | 7 | 0 | 2024-09-09 | 2024-09-15 | 7 | 100% | bar: 9/9-9/15 M to 9/9-9/15 F
1.3 | Use Case Scenarios/Diagrams | Robert, Jason, Nika | 7 | 7 | 0 | 2024-09-16 | 2024-09-22 | 7 | 100% | bar: 9/16-9/22 M to 9/16-9/22 F
2 | Project Definition/Planning |  | 8 | 8 | 0 |  |  |  | 100%
2.1 | Project Plan | Robert | 7 | 7 | 0 | 2024-09-09 | 2024-09-15 | 7 | 100% | bar: 9/9-9/15 M to 9/9-9/15 F
2.2 | Workload Breakdown/Initial Task Assignments | Robert, Jason, Nika | 1 | 1 | 0 | 2024-09-09 | 2024-09-09 | 1 | 100% | bar: 9/9-9/15 M
3 | Project Design |  | 140 | 140 | 0 |  |  |  | 100%
3.1 | System Architecture | Robert | 14 | 14 | 0 | 2024-09-23 | 2024-10-06 | 14 | 100% | bar: 9/23-9/29 M to 9/30-10/6 F
3.2 | Component Specification | Jason | 14 | 14 | 0 | 2024-09-23 | 2024-10-06 | 14 | 100% | bar: 9/23-9/29 M to 9/30-10/6 F
3.3 | Interface Specification | Jason | 28 | 28 | 0 | 2024-09-23 | 2024-10-20 | 28 | 100% | bar: 9/23-9/29 M to 10/21-10/27 F
3.4 | Communication Plan | Robert | 28 | 28 | 0 | 2024-09-23 | 2024-10-20 | 28 | 100% | bar: 9/23-9/29 M to 10/21-10/27 F
3.5 | Algorithim Design | Robert | 28 | 28 | 0 | 2024-09-23 | 2024-10-20 | 28 | 100% | bar: 9/23-9/29 M to 10/21-10/27 F
3.6 | Testing and Design Specifications | Jason | 28 | 28 | 0 | 2024-09-23 | 2024-10-20 | 28 | 100% | bar: 9/23-9/29 M to 10/21-10/27 F
4 | Project Coding |  | 84 | 84 | 0 |  |  |  | 100%
4.1 | Application Code: Server | Robert/Nika | 28 | 28 | 0 | 2024-10-21 | 2024-12-08 | 49 | 100% | bar: 10/28-11/3 M to 12/9-12/15 M
4.2 | Application Code: Browser | Jason | 28 | 28 | 0 | 2024-10-21 | 2024-12-08 | 49 | 100% | bar: 10/28-11/3 M to 12/9-12/15 M
4.3 | Application Code: Database | Robert/Jason | 28 | 28 | 0 | 2024-10-24 | 2024-11-24 | 32 | 100% | bar: 10/28-11/3 M to 12/9-12/15 M
5 | Project Testing |  | 27 | 27 | 0 |  |  |  | 100%
5.1 | Unit Testing | Robert, Jason, Nika | 7 | 7 | 0 | 2024-12-02 | 2024-12-08 | 7 | 100% | bar: 12/2-12/8 M to 12/9-12/15 T
5.2 | Component Testing | Robert, Jason, Nika | 7 | 7 | 0 | 2024-12-02 | 2024-12-08 | 7 | 100% | bar: 12/2-12/8 M to 12/9-12/15 T
5.3 | System Testing | Robert, Jason, Nika | 7 | 7 | 0 | 2024-12-02 | 2024-12-08 | 7 | 100% | bar: 12/2-12/8 M to 12/9-12/15 T
5.4 | User Testing | Robert, Jason, Nika | 6 | 6 | 0 | 2024-12-09 | 2024-12-13 | 5 | 100% | bar: 12/2-12/8 M to 12/9-12/15 F
*NOTE: We Each Have Inputs on All Tasks and Time Estimates are not Fixed

## User Stories or Tasks
USER STORIES OR TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
Title | Task description | Name | MM/DD/YY

## Dropdown Keys - DO NOT DELETE
Dropdown Keys - DO NOT DELETE
STATUS KEY | WORK ESTIMATE IN HOURS | PRIORITY KEY
Complete | 1 | High
Overdue | 2 | Medium
In Progress | 4 | Low
Not Started | 8
16
24
40
80